CO-PRODUCTION AND COLLABORATION AGREEMENT

“Zaheera Boomgaard Documentary”

(“Project”)

INFINITY FILMS (PTY) LTD

REGISTRATION NO. 2014/263850/07

Address: 23 Mountain Silver Drive

Welgevonden,

Stellenbosch

And

IDEA CANDY (PTY) LTD

REGISTRATION NO. 2015/046121/07

Address: Greenstone House, Stonemill Office Park

300 Acacia Avenue, Randburg

INDEX

No.	Description									Page

- Preamble, parties, context and purpose of agreement				2

- Definitions and Interpretation							6

- Roles, Responsibilities and Creative/Editorial Authority				10

- Netflix Requirements, Approval Rights, Legal Compliance, Risk

Management, Ethical Standards and Security Obligations			14

- Contributor Management, Access, Consents, Releases and Duty of Care		18

- Intellectual Property, Rights Ownership, Archival Licensing and Chain of Title	23

- Financial Structure, Budgets, Payment Terms, 50/50 Producer-fee

Sharing, SPV Governance and Accounting					28

- Liability, Warranties, Indemnities, Insurance and Risk Allocation			33

- Confidentiality, Data Protection, Investigation Security and Handling of

Sensitive Material								38

- Netflix Deliverables, Development Deliverables, Reporting Obligations and

Creative/Legal Sign-Off Procedures						42

- Comprehensive Risk Management Framework, Legal Risk Mitigation and

Ethical Compliance								47

- Term, Suspension and Termination						51

- Breach, Remedies and Specific Performance  					53

- Force Majeure   								53

- Dispute Resolution, Governing Law and Jurisdiction   				54

- Notices and Domicilia   								55

- Cession, Assignment and Delegation  						56

- Relationship Between the Parties  						56

- General 									56

CO-PRODUCTION AND COLLABORATION AGREEMENT

“Zaheera Boomgaard Documentary”

(“Project”)

Between:

INFINITY FILMS (PTY) LTD

REGISTRATION NO. 2014/263850/07

Address: 23 Mountain Silver Drive

Welgevonden,

Stellenbosch

duly represented by Albert Snyman, in his capacity as Director

(“Infinity Films”)

And

IDEA CANDY (PTY) LTD

REGISTRATION NO. 2015/046121/07

Address: Greenstone House, Stonemill Office Park

300 Acacia Avenue, Randburg

duly represented by Willem Du Plessis Steyn in his capacity as Director

(“Idea Candy”)

1. 	PREAMBLE, PARTIES, CONTEXT AND PURPOSE OF AGREEMENT

1.1 	This Co-Production and Collaboration Agreement (“the Agreement”) is concluded between Infinity Films (Pty) Ltd, a private company incorporated under the laws of the Republic of South Africa with registration number 2014/263850/07, having its principal place of business at 23 Mountain Silver Drive, Welgevonden, Stellenbosch, duly represented for purposes of this Agreement by Albert Snyman in his capacity as Director (hereinafter referred to as “Infinity Films”), and Idea Candy (Pty) Ltd, a private company incorporated under the laws of the Republic of South Africa with registration number 2015/046121/07, having its principal place of business at Greenstone House, Stonemill Office Park, 300 Acacia Avenue, Randburg, duly represented by Willem du Plessis  Steyn (hereinafter referred to as “Idea Candy”). Infinity Films and Idea Candy shall hereinafter be referred to jointly as “the Parties” and individually as “a Party”.

1.2 	The Parties record that Infinity Films has conceived in conjunction with Susan Puren a documentary based on the actions of Zaheera Boomgaard, of a length yet to be determined (the “Project”). Infinity Films has requested Idea Candy to join the Project as co-producers.

1.3 	The Parties further record that the conceptualisation and development of the Project has involved research into (i) historic and contemporary criminal events, (ii) forensic investigations, (iii) court proceedings and state evidence, (iv) police archives, (v) witness testimonies, (vi) forensic psychiatric evaluations, (vii) family histories of trauma and violence, (viii) digital, metadata and cellular analysis, and (ix) emotional accounts of victims, survivors, journalists, close associates and investigators. Accordingly, the Project concerns highly sensitive material that requires rigorous legal compliance, ethical diligence, technical precision, journalistic honesty and evidentiary integrity.

1.4 	Netflix, acting as the potential broadcaster and commissioner of the Project (“the Broadcaster”), has stipulated that, prior to the conclusion of any Development Agreement or Production Agreement with the Parties, there must be a fully executed and comprehensive co-production agreement between Infinity Films and Idea Candy that sets out (i) the creative, editorial and managerial responsibilities of each Party, (ii) the legal, ethical and compliance duties required during development and production, (iii) financial structures for development and production, (iv) allocation of rights and intellectual property, (v) attention to Netflix’s security and delivery standards, and (vi) the governance structure applicable to any Special Purpose Vehicle (“SPV”) to be incorporated upon commissioning.

1.5 	The Parties acknowledge that Netflix’s requirements include, inter alia, the following obligations: adherence to Netflix’s technical delivery standards, including but not limited to IMF delivery specifications, original frame rate and aspect ratio preservation, maintenance of source materials, compliance with Netflix’s Studio Information Security Protocols (including encryption, controlled access, digital asset protection, secure transfer, auditability and breach reporting), compliance with Netflix’s ethical standards for documentary storytelling, compliance with multi-jurisdictional privacy and data-protection laws, compliance with defamation, contempt and fair-trial principles, and robust legal vetting of all content prior to picture lock.

1.6 	The Parties record further that the Project’s original creative concept is developmental and indicative in nature and may be refined or adapted during Development Phase, Production Phase and Post-Production Phase, subject to the approval processes set out in this Agreement and any commissioning agreement with the Broadcaster.

1.7 	The Parties accordingly wish to enter into this Agreement in order to establish a complete, integrated, and binding framework governing the development, pre-production, production and post-production of the Project, and to ensure that the Project is executed to the highest international standards of creative integrity, technical excellence, legal compliance, contributor safety, ethical responsibility, cultural sensitivity, narrative clarity, and editorial accuracy.

1.8 	The Parties agree that this Agreement shall govern all collaborative activities between them from the commencement of development and shall regulate every aspect of their working relationship until such time as the Project is either (i) fully delivered to Netflix following commissioning, (ii) terminated by Netflix or the Parties in accordance with this Agreement, or (iii) not commissioned, in which event the provisions governing development, intellectual property, confidentiality and rights survive as provided herein.

1.9 	The Parties acknowledge that the Project concerns subject matter of significant public interest, including allegations of multiple murders, suspicious deaths, disappearances, fraud, forgery, identity manipulation, family trauma, psychological complexity and systemic investigative failures. Given the magnitude of these issues, the Parties agree that all creative, editorial, legal and operational decisions must reflect the seriousness of the material and must comply fully with applicable laws, industry standards and Netflix production ethics.

1.10 	The Parties recognise the importance of a trauma-informed and dignity-respecting approach to all contributors, including but not limited to survivors, victims’ families, neighbours, friends, investigators, forensic experts, police officers, and the journalist who has devoted years to uncovering the facts of the case, Ms Susan Purén, whose investigative work provides the foundation for much of the Project’s access and evidentiary material.

1.11 	The Parties recognise that the story is currently envisaged as being told with the participation and on-camera contributions of certain individuals who may serve as emotional, narrative and investigative anchors. Engagement of such individuals shall remain subject to their willingness to participate, availability, legal and ethical considerations and the Broadcaster’s requirements. The Parties agree that this Agreement shall regulate the way in which contributors are approached, contracted, portrayed and protected, it being recorded that there is no guarantee that any particular individual will ultimately appear in the Project or appear in any particular manner.

1.12

The Parties acknowledge that Netflix requires that all key personnel proposed for the Project are subject to its approval, including the Director, Heads of Department, Editors, Archive Researchers, Legal Advisors and any other leading creative or technical personnel. Netflix approval rights shall therefore be incorporated as binding provisions of this Agreement.

1.13 	The Parties agree that this Agreement is intended not merely to set out minimum requirements but to codify a comprehensive, premium-grade, internationally compliant co-production framework that reflects the seriousness, complexity and sensitivity of the Project and anticipates the risk areas associated with true-crime documentary storytelling.

1.14 	The Parties further agree that any commissioning of the Project shall require the immediate formation of a Special Purpose Vehicle (“SPV”) jointly owned by the Parties in equal shares, through which all production contracting, financing, accounting, auditing, payment flows and reporting shall occur. This Agreement shall continue to regulate the Parties’ relationship until the execution of the SPV Shareholders’ Agreement.

1.15 	The Parties record that they bear joint responsibility to ensure that the Project is delivered in accordance with Netflix’s technical specifications, editorial standards, narrative expectations, legal requirements, digital security protocols, and ethical guidelines. Any failure to meet these obligations constitutes a material breach.

1.16 	The Parties therefore conclude this Agreement in order to comprehensively regulate their legal, financial, editorial, creative, ethical and operational collaboration in respect of the Project.

1.17	Creative Flexibility and Non-Binding Editorial Descriptions

The Parties record that all references in this Agreement to the logline, editorial concept, tone, world, emotional anchors, narrative threads, episode titles, episode content, locations, contributors and similar creative or editorial elements reflect the Parties’ current intentions as at the Signature Date only. Such descriptions are provided for contextual and planning purposes and shall not constitute warranties, conditions or immutable obligations as to the final form, structure or contents of the Project.

1.17.1 Non-Binding Nature of Netflix Guidance

Any reference in this Agreement to editorial approaches, investigative principles, development intentions, production practices, contributor strategies, or other guidance provided by Netflix shall constitute non-binding guidance only. Netflix’s creative, editorial and business decisions shall remain entirely subject to prevailing circumstances and to its sole discretion at each stage of development and production.

1.18	The Parties acknowledge that, subject to compliance with the Broadcaster’s reasonable requirements and applicable law, the creative approach, narrative structure, episode framework, list of contributors and treatment may evolve during Development, Production and Post-Production. No Party shall be deemed to have guaranteed the inclusion of any storyline, interviewee, location, format, episode structure or other creative element in the final delivered programme.

1.19 	Incorporation by Reference of Netflix Development Agreement

The Parties acknowledge that the terms of the Netflix Development Agreement for “The Zaheera Boomgaard Documentary” shall govern all rights, obligations, ownership structures, deliverables, approval rights, key personnel requirements and development-phase processes. To the extent of any conflict between this Agreement and the Netflix Development Agreement, the provisions of the Netflix Development Agreement shall prevail.

2. 	DEFINITIONS AND INTERPRETATION

2.1 	For purposes of this Agreement, unless the context indicates otherwise, the terms set out in this clause shall bear the following meanings, and such definitions shall apply to all clauses, sub-clauses, provisions, obligations and rights contained herein.

2.2 	“Agreement” means this Co-Production and Collaboration Agreement, including all clauses, sub-clauses, defined terms and incorporated provisions contained herein, which collectively constitute the full, binding, and final expression of the Parties’ collaborative relationship from development through final delivery, except where expressly superseded by a subsequent written agreement.

2.3 	“Project” means the factual audiovisual production relating to the life and alleged criminal conduct of the Subject, as further described in the Infinity Films’ current creative concept for the Project. The Parties record that such creative concept is developmental and may be refined or amended from time to time in accordance with this Agreement and any commissioning agreement with the Broadcaster.

2.4 	“The Subject” means the individual whose life, identities, conduct, psychological history, interpersonal relationships, criminal allegations, proven offences, and suspected additional crimes form the central focus of the Project, being the woman known variously as Zaheera Boomgaard, Penny Basdeo, Geetha, Penny Wookey, Penny Boomgaard, Zaheera Wookey, Sabrina Boomgaard, and any other identities she may have assumed historically.

2.5 	“Broadcaster” means Netflix, including any of its parents, affiliates, subsidiaries, successors or authorised representatives, and any entity designated by Netflix to act in respect of commissioning, approving, financing, supervising or receiving deliverables for the Project.

2.6 	“Deliverables” means all creative, editorial, legal, research, technical, financial, production, post-production, archival, and administrative materials required by the Broadcaster, including but not limited to: the narrative outline; the editorial story structure; the unique selling proposition; the synopsis; the non-linear narrative map; the timeline overview; the list of confirmed and unconfirmed contributors; the archive access list; the access-provenance documents; the list of State evidence; the legal opinion on risks; the director’s vision; the proposed Heads of Department; the production counsel briefing document; the detailed questionnaire document; raw footage; working files; final masters; IMF packages; audio stems; graphics elements; and all other materials customarily required in high-end documentary production.

2.7 	“Executive Producers” or “EPs” means Mr Albert Snyman (Infinity Films) and Mr Willem du Plessis Steyn (Idea Candy), who collectively hold the highest creative, editorial, ethical, legal and managerial authority within the Project, and whose unanimous approval is required for all major decisions as defined in Clause 2.20 of this agreement.

2.8

“Creative Team” means all persons appointed by either Party to render creative, research, editorial, investigatory or narrative services to the Project, including but not limited to the Executive Producers, the Series Producer, the Writers, the Director, the Research Team, the Archive Research Team, the Editor, the Assistant Editors, the Forensic Analyst consultants, the Story Consultants, the Narrative Advisors, and any additional editorial specialists.

2.9 	“Development Phase” means the period commencing upon signature of this Agreement and continuing until (i) the Broadcaster elects to commission the Project; (ii) the Broadcaster rejects the Project; or (iii) the Project is terminated in accordance with this Agreement, during which period the Parties undertake all research, writing, conceptualisation, access-confirmation, narrative structuring, legal risk assessment, budgeting, scheduling, team assembly, and deliverable preparation required to enable commissioning.

2.10 	“Pre-Production Phase” means the period following commissioning but before commencement of principal photography, during which the Parties refine the script, secure locations, finalise contracts, refine access agreements, confirm budgets and schedules, prepare technical workflows, establish the SPV bank accounts, and obtain Broadcaster approval of all essential creative and technical elements.

2.11 	“Production Phase” means the period during which principal photography, interviews, recreations (if any), archival acquisition, forensic filming, location filming, contributor interviews, and all other on-camera activities are undertaken.

2.12 	“Post-Production Phase” means the period during which all editorial assembly, offline editing, online editing, colour grading, sound design, sound mix, subtitles, graphics creation, legal review, fact-checking, conformity to Netflix technical standards, and final delivery of IMF and source materials occurs.

2.13 	“Archive Materials” means all materials including photographs, video footage, phone recordings, CCTV files, audio files, paper documents, State evidence, investigative diaries, notes, forensic records, bank metadata, court transcripts, digital logs, and any other materials relevant to the Project requiring legal clearance prior to use.

2.14 	“State Evidence” means all materials produced or held by the South African Police Service, the National Prosecuting Authority, forensic laboratories, courts or any state investigative body, including but not limited to photographs, autopsy records, audio recordings, digital files, case dockets, metadata, forensic analyses and statements.

2.15 	“Contributor” means any individual participating in the Project on- or off-camera, whether as an interviewee, narrator, witness, investigator, family member, survivor, analyst, consultant or other participating voice whose contributions must be governed by a Contributor Release.

2.16 	“Technical Specifications” means all Netflix-delivery requirements including but not limited to IMF packaging, full-resolution source materials, audio stems, EBU-R128 loudness compliance, metadata requirements, original framerate preservation, aspect ratio regulations, graphics delivery, subtitles and captions, QC processes, and the provision of all required technical documentation.

2.17 	“Security Protocols” means the Netflix Studio Information Security Protocols and all other digital and physical security requirements including encryption, access control, password discipline, breach reporting, secure file transfer, device management, and restricted access to sensitive materials.

2.18 	“Data Protection Laws” means all applicable legislation governing personal information and data, including the Protection of Personal Information Act 4 of 2013 (POPIA), the United Kingdom General Data Protection Regulation (UK GDPR), and any equivalent or applicable foreign data protection regime.

2.19 	“SPV” means the Special Purpose Vehicle to be incorporated jointly by the Parties upon commissioning, through which all contractual, financial, accounting, payroll, procurement, vendor engagement, invoicing and production operational activities shall be conducted.

2.20 	“Major Decision” means any decision materially affecting (i) the editorial direction, (ii) the narrative structure, (iii) the portrayal of the Subject, (iv) treatment of emotional anchors, (v) ethical risks, (vi) legal risk exposure, (vii) any depiction of alleged but unproven criminal acts, (viii) budget or financial exposure, (ix) team composition, or (x) compliance with Netflix requirements, and which therefore requires unanimous approval of the Executive Producers.

2.21 	Any reference to a statute shall include the statute as amended, replaced or re-enacted from time to time, and any reference to a Party includes that Party’s permitted assignees or successors in title.

2.22 	Clause headings are inserted for convenience and shall not affect interpretation.

2.23 	Where a term is defined in the singular, it includes the plural and vice versa.

2.24 	This Agreement shall be interpreted in accordance with its plain meaning and without regard to the contra proferentem rule.

3.

ROLES, RESPONSIBILITIES AND CREATIVE/EDITORIAL AUTHORITY

3.1 	General Principles Governing Roles and Collaboration

3.1.1 	The Parties agree that the Project requires a clear, structured and legally binding allocation of roles, responsibilities, creative authority, editorial oversight, financial control, operational management, and risk-mitigation obligations, which shall be strictly adhered to during all phases of the Project.

3.1.2 	The Parties acknowledge that, due to the highly sensitive true-crime nature of the Project, each creative and operational role carries responsibilities that extend beyond ordinary documentary production, including heightened ethical scrutiny, meticulous legal compliance, profound contributor care obligations, rigorous fact-checking, protection of sensitive evidence, and adherence to Netflix’s safety, security and editorial-approval protocols.

3.1.3 	The Parties agree that the core leadership structure of the Project shall consist of:
(a) 	Executive Producers (Infinity Films and Idea Candy);

(b) 	Series Producer (Idea Candy);

(c) 	Line Producer (Idea Candy);

(d) 	Writers (Infinity Films); and

(e) 	all additional Heads of Department, who shall be appointed subject to

unanimous approval of the Executive Producers and approval by Netflix.

3.1.4 	The Parties further agree that decisions shall be categorised into:

(a) 	Major Creative and Editorial Decisions, requiring unanimous approval of the Executive Producers;

(b) 	Significant Production Decisions, requiring approval of the Executive Producers and the Series Producer; and

(c) 	Operational Production Decisions, falling within the delegated authority of the Series Producer and Line Producer, subject to compliance with the Project’s budget, schedule, editorial concept, and legal restrictions.

3.2 	Executive producers — General Authority and Oversight

3.2.1 	The Executive Producers, being Willem du Plessis Steyn (Idea Candy) and Albert Snyman (Infinity Films), shall jointly exercise the highest level of creative, editorial, legal and managerial authority within the Project, and no material decision shall be taken without their collective approval as provided herein.

3.2.2 	The Executive Producers shall serve as custodians of the Project’s editorial intent, narrative integrity, journalistic accuracy, ethical compliance and stylistic coherence throughout all phases of production.

3.2.3 	The Executive Producers shall be jointly responsible for ensuring that the Project adheres to Netflix’s requirements, including but not limited to:

(a) 	editorial and legal review;

(b) 	risk assessments;

(c) 	fact-checking and accuracy standards;

(d) 	technical delivery specifications;

(e)	digital security protocols; and

(f) 	contributor safety obligations.

3.2.4	The Executive Producers shall retain overriding approval rights over:

(a) 	the narrative structure;
(b) 	the non-linear editorial design;
(c)	 the tone and treatment of sensitive material;
(d) 	the portrayal of the Subject;
(e) 	the treatment of victims and survivors;
(f) 	the Project’s visual language;
(g) 	the appointment of the Director and all Heads of Department;
(h) 	the final script and episode structures;
(i) 	the rough and fine cuts;
(j) 	the final locked cut;
(k) 	the final delivery materials; and
(l) 	any publicity, marketing, or promotional content referencing the Project.

3.2.5 	The Executive Producers shall attend and lead weekly status meetings with the Series Producer, Line Producer and research team to:

(a) 	evaluate investigative developments;
(b) 	review progress against creative benchmarks;
(c) 	analyse story beats and emotional arcs;
(d) 	approve or amend creative direction; and
(e) 	ensure compliance with budget and timeline.

3.	3 	Executive Producer Responsibilities — Development Phase

3.3.1	During the Development Phase, the Executive Producers shall collectively:

(a) 	oversee all research, investigative and archival processes;

(b) 	evaluate and approve all story beats, emotional anchors and creative angles;

(c) 	identify and approve contributors critical to the narrative;

(d) 	ensure that contributor approaches are ethically and legally compliant;

(e) 	review all archival access requests and associated legal requirements;

(f) 	supervise the drafting of outline documents, treatment, narrative map and deliverables;

(g) 	ensure alignment of the Writers' narrative work with the editorial concept;

(h) 	manage the interface with Netflix regarding editorial and legal queries; and

(i) 	assess risks associated with portrayal of criminal allegations, unverified claims, hearsay content and sensitive material.

3.3.2	The Executive Producers shall determine the approach toward:

(a) 	the Subject’s psychological profile;

(b) 	the multi-generational trauma narrative;

(c) 	the Subject’s shifting identities;

(d) 	allegations involving historic family crimes; and

(e) 	unresolved or cold-case elements.

3.3.3 	The Executive Producers shall, through the Series Producer and Line Producer, ensure that development budget modelling complies with Netflix’s expectations and reflects all necessary creative, research and legal tasks.

3.4 	Executive Producer Responsibilities — Pre-Production Phase

3.4.1	In the Pre-Production Phase, the Executive Producers shall:

(a) 	approve all scripts, story maps and structural documents;

(b) 	engage directly with the Director to establish creative execution;

(c) 	approve all key creative treatments including graphics, music, editorial rhythms and tone;

(d) 	oversee final budget alignment and schedule confirmation;

(e) 	participate in hiring key personnel;

(f) 	approve all contributor releases, archive licences and legal documentation;

(g) 	ensure the SPV is correctly formed, resourced and legally compliant; and

(h) 	approve the workflow structure for production and post.

3.5 	Executive Producer Responsibilities — Production Phase

3.5.1 	During Production Phase, the Executive Producers shall:

(a) 	work continuously with the Director to adjust story treatment as filming reveals new insights;

(b) 	evaluate daily filming outcomes;

(c) 	approve narrative pivots necessitated by production realities;

(d) 	ensure ongoing compliance with legal and safety obligations;

(e) 	approve creative decisions regarding interviews, locations and sensitive

material;
(f) 	maintain oversight of the production budget and resource allocation;
(g) 	ensure safe handling and encryption of footage and evidence; and
(h) 	sign off on all major creative decisions arising from daily developments.

3.6 	Executive Producer Responsibilities — Post-Production Phase

3.6.1	During Post-Production Phase, the Executive Producers shall:

(a) 	engage with the Editor and Director on story arcs, revelations, sequencing and narrative logic;

(b) 	approve offline cuts, fine cuts and final cuts;

(c) 	oversee the integration of graphics, subtitles, score and online finishing;

(d) 	ensure that all legal comments from production counsel are fully addressed;

(e) 	ensure that right-of-reply obligations are handled appropriately;

(f)	conduct quality-control screenings of all episodes;

(g) 	approve all PR materials, trailers and promotional assets; and

(h)	ensure final delivery meets Netflix’s delivery, QC and security specifications.

3.7

Decision-making Hierarchy and Approval Workflow

3.7.1 	The following decisions require unanimous approval of all Executive Producers:

(a) 	final narrative structure;
(b) 	portrayal of the Subject;
(c) 	portrayal of victims and emotional anchors;
(d) 	hire or dismissal of Director or HODs;
(e) 	structural narrative changes;
(f) 	final locked cuts;
(g) 	legal-risk decisions;
(h) 	budgetary reallocations above agreed thresholds.

3.7.2	The following decisions require approval of the Executive Producers

(a) 	scheduling changes;

(b) 	budget refinements;

(c) 	contributor management strategies;

(d) 	production logistics involving sensitive material.

4. 	NETFLIX REQUIREMENTS, APPROVAL RIGHTS, LEGAL COMPLIANCE, RISK MANAGEMENT, ETHICAL STANDARDS AND SECURITY OBLIGATIONS

4.1

General Netflix Requirements and Overriding Authority

4.1.1	The Parties acknowledge that Netflix, as the prospective Broadcaster, expects all

creative, editorial, technical, legal and operational decisions relating to the Project to be compliant with its global documentary standards. These standards include, but are not limited to, technical delivery specifications, legal-compliance expectations, editorial integrity, narrative clarity, contributor protection, data protection, security protocols, and rigorous risk-management processes.

4.1.2 	The Parties recognise that Netflix’s approval rights constitute binding contractual expectations only to the extent that such approvals relate to legal, ethical, factual, compliance and broadcast-readiness standards, and do not restrict the Parties’ ability to refine or adjust creative or editorial elements during the natural evolution of the Project.

4.1.3 	Netflix’s Sole Discretion – Development and Production

The Parties expressly acknowledge and agree that Netflix shall have sole and unfettered discretion to determine whether the Project is (i) accepted during the Development Phase, (ii) commissioned for production, and (iii) approved at each subsequent creative, editorial, technical or managerial stage. Nothing in this Agreement shall be construed as obliging Netflix to commission, produce, distribute or exploit the Project, and all development activities undertaken by the Parties are subject to Netflix’s final decision-making authority.

4.1.4 	Netflix Final Approval – Development

Netflix shall retain final and overriding approval over all Development Materials, development outcomes, creative treatments, story structures, business elements, contributor lists, proposed key personnel, archival strategies, legal reviews, and any other development-related matters. The Parties shall promptly incorporate all comments, revisions and required amendments issued by Netflix.

4.1.5 	Netflix Final Approval – Production (If Commissioned)

If the Project is commissioned for production, Netflix shall retain final approval over all execution and production matters, including without limitation all Heads of Department, the Director, production schedules, budgets, scripts, cuts, delivery elements, contributor releases, legal clearances, archival licences, risk assessments, right-of-reply processes, and all creative, editorial, operational and business decisions taken in connection with the Project.

4.2 	Netflix Truth-In-Documentary Requirements

4.2.1 	The Parties understand and accept that Netflix requires strict adherence to its “truth-in-documentary” expectations, meaning that all factual assertions, statements of historical record, allegations, timelines, character depictions, archival materials and investigative representations must be:
(a) 	verifiable;
(b) 	documented;
(c) 	supported by credible evidence;
(d) 	legally safe; and
(e)	 framed accurately within the broader context of the Project.

4.2.2 	No assertion, whether explicit or implied, may be included unless:
(a) 	it has been verified by the research team;
(b) 	it has been reviewed by production counsel;
(c) 	documentary evidence or credible testimony supports it; and
(d) 	it is presented in a manner that avoids defamation, misrepresentation or

unjustified inference.

4.3 	Legal-Compliance Expectations

4.3.1 	The Parties shall comply with all applicable laws, including but not limited to:

(a) 	South African privacy, defamation, criminal law and court-reporting rules;
(b) 	the Protection of Personal Information Act (POPIA);
(c) 	the United Kingdom General Data Protection Regulation (UK GDPR);
(d) 	international intellectual property laws;
(e) 	fair-trial principles and sub judice rules;
(f) 	copyright and archival licensing obligations;
(g) 	journalist-source protection standards;
(h) 	statutory obligations relating to State evidence.

4.3.2	 The Parties agree that any depiction of unproven allegations, investigative theories,

incomplete evidence or contested facts must be clearly contextualised, balanced and legally safe.

4.4 	Ethical Standards and True-Crime Obligations

4.4.1 	The Parties acknowledge that the Project involves deeply traumatic material including murder, violence, manipulation, and intergenerational trauma, and therefore the Project must employ a trauma-informed, dignity-respecting approach to contributors, victims, families, investigators and all individuals affected by the Subject’s actions.

4.4.2 	The Parties agree that contributors must be approached sensitively, honestly and transparently, with clear explanations of:
(a)	 their role in the Project;
(b) 	the potential emotional impact of participation;
(c)	 their options for support;
(d)	 their right to decline sensitive questions;
(e) 	their right to request breaks or pauses during interviews;
(f) 	the absence of coercion or exploitation.

4.4.3 	Vulnerable contributors, including grieving families, traumatised witnesses, elderly individuals, and the Subject’s daughter, shall be handled in accordance with trauma-informed interviewing protocols approved by Netflix.

4.5 	Netflix Security and Data-Protection Expectations

4.5.1 	The Parties agree to comply with Netflix’s Studio Information Security Protocols, including but not limited to:
(a) 	strict encryption of all footage and sensitive documents;
(b) 	password-secured systems for all digital materials;
(c) 	controlled access to raw footage and metadata;
(d) 	secure transfer of files using Netflix-authorised platforms;
(e) 	device-management protocols;
(f) 	mandatory reporting of security breaches;
(g) 	storage of sensitive evidence in locked and access-controlled environments.

4.5.2 	No raw footage, archival material, State evidence, interview files, scripts or cuts shall be transmitted via unencrypted channels, personal email accounts, unsecured drives or cloud platforms not approved by Netflix.

4.6 	Evidence Handling, Archival Materials and State Records

4.6.1 	Because the Project relies significantly on State evidence, forensic data, cellular metadata, CCTV footage, medical records, police files and court documents, the Parties agree that:
(a) 	all such material must be lawfully obtained;
(b) 	licensing or access rights must be documented;
(c) 	no restricted material may be used without written authorisation;
(d) 	all sensitive materials shall be stored in encrypted, access-controlled

environments;
(e) 	the chain of custody of evidence must be preserved.

4.6.2 	The Parties shall ensure that State evidence is contextualised responsibly, including the use of forensic diagrams, autopsy reports, case-docket records, police interviews, witness statements, and all other sensitive information.

4.7	 Right-of-Reply Obligations

4.7.1 	The Parties shall comply with Netflix’s right-of-reply expectations, requiring that individuals or entities subject to serious allegations of wrongdoing be afforded the opportunity to respond to such allegations before broadcast.

4.7.2 	Where the Subject is unable or unwilling to provide a response (including if incarcerated or represented by legal counsel), the Project shall document all efforts to offer the right of reply.

4.8	International Jurisdictional Obligations

4.8.1 	The Parties acknowledge that the Project spans multiple jurisdictions including South Africa, the United Kingdom and India. As such, all content must comply with the laws of each relevant territory.

5.	CONTRIBUTOR MANAGEMENT, ACCESS, CONSENTS, RELEASES AND DUTY OF CARE

5.1 	General Principles Governing Contributor Engagement

5.1.1 	The Parties acknowledge that the Project involves deeply sensitive subject matter, including allegations of murder, poisoning, fraud, manipulation, domestic abuse, intergenerational trauma and unresolved criminal patterns, and therefore requires the highest level of ethical care in all engagements with contributors.

5.1.2 	The Parties agree that all contributors must be approached, interviewed and portrayed in a manner that prioritises their emotional wellbeing, safety, dignity, privacy, and legal protection.

5.1.3	The Parties agree that no contributor shall be filmed or recorded without:
(a) 	a clear explanation of the Project;
(b) 	an understanding of the editorial intent;
(c) 	Informed consent;
(d) 	signed written releases; and
(e) 	compliance with all legal, ethical and Netflix requirements.

5.1.4	The Parties record that the identification of contributors and contributor categories in this Agreement reflects the current creative intent and research findings and shall not be interpreted as a commitment that any specific contributor will appear, nor that the Project will ultimately include contributions from any named individual.

5.2 	Contributor Categories

5.2.1 	For purposes of managing obligations under this Agreement, contributors shall be

categorised as follows:

(a) 	Primary Emotional Anchors — contributors who are currently envisaged as

forming the backbone of the Project, including Susan Purén, Leonie Ras, Rinie Uys, Sakeena Nicholson, and the families of victims;

(b) 	Investigative Contributors — including detectives, forensic analysts, metadata

specialists, archivists, private investigators, and police officials;
(c) 	Archive/Evidence Contributors — individuals providing personal archives,

recordings, diaries, photographs, digital logs or historic records;
(d) 	Expert Contributors — including psychologists, forensic pathologists,

handwriting analysts and legal experts;
(e) 	Peripheral or Contextual Contributors — neighbours, community members or

individuals with incidental knowledge;
(f) 	Vulnerable Contributors — including grieving families, survivors of

manipulation, traumatised witnesses, elderly individuals, minors (where

applicable), and individuals experiencing emotional or psychological fragility.

5.3 	Informed Consent and Contributor Explanation

5.3.1 	Before any engagement, contributors must be provided with a clear, truthful, accessible explanation of:
(a) 	the nature of the Project;
(b) 	its purpose and themes;
(c) 	the handling of sensitive topics;
(d) 	their role and expected contributions;
(e) 	any potential emotional impact;
(f) 	the intended Broadcaster (Netflix);
(g) 	the international reach of the documentary.

5.3.2 	The Parties shall ensure that all contributors understand:
(a) 	what they are consenting to;
(b) 	that their participation is voluntary;
(c)	that they may withdraw prior to filming;
(d)	that they may request breaks during filming;
(e) 	that sensitive areas need not be discussed if they are uncomfortable.

5.4 	Written Contributor Releases

5.4.1 	The Parties agree that no contributor may appear in the Project unless they have executed a comprehensive written Contributor Release, drafted or approved by production counsel.

5.4.2 	Each Contributor Release shall include provisions relating to:
(a) 	consent to film and record;
(b) 	use of name, image and voice;
(c) 	depiction in editorial context;
(d) 	grant of rights to the SPV and Broadcaster;
(e) 	waiver of claims to editorial or creative control;
(f) 	privacy and confidentiality acknowledgments;
(g)	 indemnities as reasonably required;
(h) 	acknowledgment of trauma-sensitive protocols.

5.4.3 	Special releases shall be used for individuals providing:
(a) 	State evidence;
(b) 	private archives;
(c) 	confidential materials;
(d) 	access to crime scenes or personal property.

5.5 	Vulnerable Contributors & Trauma-Informed Engagement

5.5.1	 The Parties acknowledge that several contributors, including certain family members, survivors, elderly persons, emotionally fragile individuals, and persons historically manipulated by the Subject, may be significantly affected by recounting traumatic experiences.

5.5.2 	The Parties agree to adhere to a trauma-informed interviewing framework, which includes:
(a) 	using non-leading, non-coercive interview techniques;
(b) 	avoiding aggressive or sensational questions;
(c) 	allowing breaks upon request;
(d) 	permitting contributors to decline sensitive topics;
(e) 	ensuring the presence of a support person where appropriate;
(f) 	avoiding traumatisation or emotional distress;
(g) 	discontinuing interviews where emotional safety is compromised.

5.5.3	 For contributors who express distress or uncertainty, the Series Producer shall offer:
(a) 	additional explanation;
(b) 	rescheduling;
(c) 	referral to support resources;
(d) 	reduced questioning;
(e) 	Interview termination where required.

5.6 	Engagement of Victims’ Families

5.6.1 	The Parties acknowledge that the families of victims, including without limitation and only where appropriate and available, Genevieve Antoun, Aruna Premji and Alida Heine, are central contributors who’s emotional and narrative participation must be managed with exceptional sensitivity.

5.6.2	 The Parties shall ensure that these contributors:
(a) 	are approached respectfully;
(b) 	understand the full narrative purpose;
(c) 	are given the option to prepare emotionally;
(d) 	have full clarity on how their testimony will be incorporated.

5.6.3	No family member shall be approached without prior approval of the Executive Producers and the Series Producer.

5.7	 Engagement of Investigators, Forensic Officers and Experts

5.7.1 	Contributors such as Brigadier (Ret.) Leonie Ras, Captain Werner van den Bergh, Lt Col. Flip Claassen, Colonel Hoosen Samaad, Warrant Officer Kevin Govender, Pieter White, Lt-Col Mmolawa and others may be approached and interviewed where appropriate in a manner that accurately reflects the investigative integrity, factual detail, and procedural realities of their involvement.

5.7.2 	All factual representations taken from their testimony must be independently verified through research or documentation.

5.8 	Access to Archives, Digital Materials and Private Collections

5.8.1 	Where contributors provide access to personal archives, diaries, voice notes, digital files, WhatsApp messages, photographs or historic materials, the Parties shall ensure:

(a) 	written permission is obtained;
(b) 	data-protection requirements are met;
(c) 	sensitive personal information is handled securely;
(d) 	materials are stored in encrypted controlled-access systems.

5.9	Filming in Sensitive Environments

5.9.1 	When filming in environments associated with trauma, grief, or criminal events — including former residences of the Subject, locations where bodies were discovered, gravesites, or homes of victims — the Parties shall ensure:
(a) 	dignity and respect are maintained;
(b) 	no sensationalism is employed;
(c) 	adequate permissions are obtained;
(d) 	filming is conducted quietly and safely;
(e) 	Netflix’s ethical standards are upheld.

5.10 	Confidentiality and Protection of Contributors

5.10.1 	The Parties shall ensure that no contributor is identifiable beyond the scope of the Project without explicit consent.

5.10.2 	Sensitive information such as:
(a) 	residential addresses;
(b) 	minors’ identities;
(c) 	personal contact information;
(d) 	medical histories;
(e) 	unverified allegations;
 	shall not be disclosed unless legally permissible and editorially justified.

5.11	Right to Withdraw Prior to Filming

5.11.1 	Contributors may withdraw from participation prior to the commencement of filming without penalty.

5.11.2 	Once filmed, withdrawal may only be honoured where:
(a) 	legally permissible;
(b) 	ethically appropriate;
(c) 	consistent with Netflix requirements;
(d) 	not materially damaging to the Project.

5.12 	Interpreters, Cultural Sensitivity and Multilingual Participation

5.12.1	Where contributors speak in isiZulu, Hindi, Urdu, Gujarati, Afrikaans, English or other

languages, the Parties shall ensure:

(a) 	accurate interpretation;

(b) 	cultural sensitivity;

(c) 	non-distortion of meaning;

(d) 	correct subtitle translation.

5.13 	Special Provisions For the Subject

5.13.1 	If the Subject or her representatives are approached for a right-of-reply or interview, all interactions must comply with:
(a) 	legal counsel’s guidance;
(b) 	prison or psychiatric facility protocols;
(c)	 Netflix requirements for high-risk contributors;
(d) 	rules governing incarcerated or medically detained individuals.

5.13.2 	Under no circumstances may the Subject be paid for participation.

6. 	INTELLECTUAL PROPERTY, RIGHTS OWNERSHIP, ARCHIVAL LICENSING AND CHAIN OF TITLE

6.1 	General Principles of Intellectual Property Ownership

6.1.1 	The Parties acknowledge that the successful commissioning of the Project by Netflix requires the establishment, maintenance and delivery of a complete and undisputed Chain of Title, demonstrating clear, exclusive, and unencumbered ownership of all rights necessary to produce, exploit, distribute and deliver the Project.

6.1.2 	The Parties agree that the Project shall constitute a wholly original audiovisual work, and that all rights created through the development, pre-production, production and post-production phases shall vest exclusively in the Special Purpose Vehicle (“SPV”), which shall be jointly owned by Infinity Films and Idea Candy in equal shares.

6.1.3 	Until such time as the SPV is incorporated, each Party shall assign to the SPV — automatically and without further compensation — all intellectual property, materials, contributions, concepts, scripts, footage, graphics, designs, and creative work related to the Project.

6.1.4 	Chain and Flow of Rights to Netflix

The Parties agree that upon commissioning by Netflix, all rights in and to the Project, including all Development Materials, Production Materials, Derivative Materials, underlying rights, and all associated intellectual property created by either Party or any contributor, shall flow through the SPV solely for administrative purposes and shall ultimately vest in Netflix pursuant to the Development Agreement and any Commissioning Agreement entered into with Netflix. The SPV’s ownership shall be custodial in nature, solely for the purpose of effecting production, and shall not derogate from Netflix’s ultimate and exclusive ownership of the Project and all rights therein.

6.2 	Ownership of Development Materials

6.2.1 	All materials created during the Development Phase, including research documents, outlines, treatments, scripts, structural maps, interview frameworks, character analyses, legal opinions, archive lists, access documents and deliverables, shall be owned jointly by the Parties until the SPV is incorporated.

6.2.2 	Upon incorporation of the SPV, each Party shall execute a formal written assignment transferring all rights in such materials to the SPV.

6.2.3 	The Parties warrant that they shall not create or use any development materials for any other project or for any competing documentary, adaptation, article, podcast, series or creative work.

6.2.4 	Ownership of Development Materials Upon Non-Commissioning

If Netflix elects not to commission the Project into production, all Development Materials and all rights therein shall remain the exclusive property of Netflix in accordance with the Development Agreement, subject only to any reversion of rights expressly agreed to by Netflix in writing.

6.3 	Copyright in Video, Audio, Graphic and Written Materials

6.3.1 	All footage, audio recordings, interviews, recreations (if any), graphics, animation, photographs, writings, designs, translations, subtitles, metadata logs, transcriptions, research notes, edit files, project files, cuts, sound mixes and all other creative or technical materials created in connection with the Project shall vest exclusively in the SPV.

6.3.2 	No Party shall claim individual authorship, ownership or control over any such materials, save for moral-rights acknowledgments expressly waived in terms of this Agreement.

6.4 	Rights Granted by Contributors

6.4.1	Each Contributor shall grant to the SPV, and, through the SPV, to the Broadcaster.  a perpetual, worldwide, irrevocable and royalty-free licence which authorises the SPV and the Broadcaster to film, record and photograph the Contributor; to reproduce, exhibit and otherwise use the Contributor’s voice, likeness and spoken or written statements; to edit, adapt, dub, subtitle, translate or otherwise modify the Contributor’s recorded contribution in any manner required for the creative or technical needs of the Project; to exploit the Contributor’s recorded contribution in all forms of media now known or hereafter developed, for the duration of copyright; and to use the Contributor’s name, likeness and biographical information for all promotional, marketing and related purposes connected with the Project.

6.4.2	Every Contributor Release shall expressly provide that the Contributor waives any right to exercise editorial control over the manner in which their contribution is used; any right to seek injunctive relief restraining the use, distribution or publication of their contribution; any claim relating to defamation where the relevant content has been produced in a manner that is fair, balanced and subjected to legal review; and any claim arising from the contextualised or edited use of their appearance, likeness or statements within the Project.

6.4.3	Any Contributor who provides archival material, digital logs, diaries, personal notes,

electronic messages, voice notes or other private records shall warrant that they possess the lawful authority to supply such material to the SPV and to grant the rights required for its unrestricted use within the Project.

6.5 	State Evidence, Archive Licensing and Third-Party Rights

6.5.1	The Parties acknowledge that the Project will rely extensively on archival materials and third-party content, including but not limited to police photographs, forensic reports, CCTV recordings, cellular-phone records, State evidence, news footage, family archives, court transcripts, digital communication logs, WhatsApp and other social-media screenshots, historic photographs and handwritten notes or letters, all of which must be lawfully sourced and correctly licensed.

6.5.2	The Parties agree that each category of archival, evidentiary or third-party material incorporated into the Project shall be lawfully licensed and supported by written agreements, chain-of-title documentation, provenance information and legal clearance confirming that the SPV holds all rights required for the unrestricted worldwide use of such materials.

6.5.3	Where State evidence is included in the Project, the Parties undertake to obtain all permissions required under applicable legislation and regulatory frameworks, which may include the Criminal Procedure Act, the applicable protocols of the South African Police Service, any court-ordered restrictions applicable to such materials, and any data-protection laws such as POPIA or the United Kingdom GDPR, should the materials originate from those jurisdictions.

6.5.4	The Parties further agree that all archival and State-derived materials shall be stored, transmitted and handled strictly in accordance with Netflix’s security and technical-protection protocols, which include encrypted storage, restricted access to authorised personnel only, the use of secure transmission platforms and the maintenance of complete, digitally recorded chain-of-custody logs.

6.6 	Moral-Rights Waivers

6.6.1	Every individual who contributes a creative, artistic or intellectual work to the Project, including, without limitation, Writers, Editors, Directors, Researchers, Graphic Designers, Composers, Musicians and Animators, shall waive any moral rights they may otherwise have, including the right to be attributed as the author of any such work, the right to object to any editing, adaptation or modification of their contribution, the right to object to contextual use of their contribution within the Project and the right to claim any alleged breach of integrity in circumstances where the content has been legally vetted.

6.6.2	The Parties acknowledge that this waiver is required in order to ensure that Netflix may broadcast, adapt, market, translate, re-format and distribute the Project globally, across all formats and languages, without restriction or future claim.

6.7 	Exclusive Rights Granted to Netflix Upon Commissioning

6.7.1	Upon Netflix commissioning the Project, the Parties agree that the SPV shall grant Netflix an exclusive, worldwide licence permitting Netflix to exploit the Project in all forms of media and modes of distribution, including but not limited to streaming, broadcasting, licensing, distributing, using excerpts for promotional purposes, dubbing in any language, creating derivative works, exploiting ancillary materials, screening the Project at festivals and exhibiting the Project publicly in any territory.

6.7.2	Netflix shall further be entitled to all ancillary rights necessary to enable global release and exploitation, including digital-distribution rights, rights to create and distribute social-media content, rights to use clips for press, publicity and marketing, rights to permit educational or law-enforcement screenings, and merchandising rights to the extent that such rights are applicable and commercially exploited.

6.8 	Right to Adapt, Edit and Reformat

6.8.1	Netflix shall have the right to edit, adapt, compress, expand, localise, dub, subtitle or reformat the Project where necessary to comply with the legal requirements of any jurisdiction, the cultural expectations of different territories, the censorship requirements of particular markets or the technical specifications of various platforms or devices.

6.8.2	Neither Party shall object to such adaptations, nor shall either Party asserts any claim for additional compensation based on Netflix’s exercise of these rights, beyond the amounts expressly agreed in this Agreement.

6.9 	Rights in Production and Project Data

6.9.1	All production data generated or collected during the development, production or post-production phases, including but not limited to metadata, edit logs, edit timelines, raw footage, proxy files, audio stems, graphics source files and all related production documentation, shall vest exclusively in the SPV immediately upon creation.

6.9.2	No Party shall store, retain, transport or duplicate sensitive production data on personal devices, unapproved external drives or non-authorised cloud platforms, and all such data shall be handled strictly in accordance with Netflix’s security protocols.

6.10 	Rights in Music, Graphics and Other Creative Works

6.10.1	All music, graphics, animations, title sequences, typographical designs, visual treatments and any other creative works commissioned for the Project shall be created pursuant to written work-made-for-hire arrangements, and all rights, title and interest in such works shall be assigned exclusively to the SPV.

6.10.2	Where pre-existing music is licensed for inclusion in the Project, the relevant licences must grant worldwide, perpetual rights for all forms of media and for all modes of exploitation associated with the Project.

6.11 	Chain of Title Package for Netflix

6.11.1	The Parties shall compile, maintain and continuously update a complete Chain of Title Package that includes, without limitation, the corporate formation documents of the Parties and the SPV; all executed Contributor Releases; all archive licences; all permissions for the use of State evidence; all assignments of creative works; composer, director, writer and HOD agreements; proof of ownership of all development materials; all legal-opinion letters; and written confirmation of legal sign-off from Production Counsel.

6.11.2	Netflix shall have the right, at any time and without limitation, to audit the Chain of Title Package to ensure that all rights have been properly secured and documented.

6.11.3 Netflix Approval – Rights Flow

Any agreement, licence, engagement, contributor release, assignment, acquisition of archival material, or other rights-affecting instrument shall not be considered valid for purposes of the Chain-of-Title Package unless it is drafted in a form compliant with Netflix’s requirements and approved by Netflix in writing.

6.12 	Prohibition on Unauthorised Use of Materials

6.12.1	No Party shall use, publish, license, distribute, disclose, repurpose or otherwise exploit any footage, archival material, research findings, production materials or creative elements associated with the Project for any external or unrelated purpose,  including, without limitation, other documentaries, dramatic adaptations, podcasts, journalistic articles or derivative works, without the prior written approval of both the SPV and Netflix.

7. 	FINANCIAL STRUCTURE, BUDGETS, PAYMENT TERMS, 50/50 PRODUCER-FEE SHARING, SPV GOVERNANCE AND ACCOUNTING

7.1 	General Financial Principles

7.1.1 	The Parties agree that the financial management of the Project shall be conducted with full transparency, accountability, accuracy, and compliance with generally accepted accounting standards, Netflix’s financial control policies, and any applicable statutory obligations.

7.1.2 	The Parties shall jointly ensure that all financial systems, cost trackers, budgets, projections, reconciliations, purchase orders, contracts, payrolls, invoices and transaction records are accurate, auditable, and preserved for the period required by law and by Netflix.

7.1.3 	The Parties expressly agree that all payments received from Netflix, whether for development or production, shall be routed exclusively into the bank accounts of the SPV once established, and that no Party may receive or disburse Netflix funds through any other account or mechanism.

7.2 	Special Purpose Vehicle (SPV) — formation and governance

7.2.1	Upon the commissioning of the Project by Netflix, the Parties shall immediately establish a Special Purpose Vehicle (“SPV”) as a private company incorporated under South African law, and the Parties agree that Infinity Films and Idea Candy shall each hold fifty percent (50%) of the issued share capital of that entity.

7.2.2	The Parties further agree that the SPV shall function as the exclusive legal entity responsible for entering into all contractual relationships relating to the Project, including the commissioning agreement with Netflix; receiving, managing and accounting for all payments received from Netflix; contracting and engaging all crew members, cast, suppliers and service providers; owning and administering all intellectual property rights in the Project; maintaining and controlling all bank accounts established for the Project; administering all payroll processes and production accounting; paying all production-related expenses; contracting all required legal counsel, insurance providers, music licensors, archive licensors and other necessary vendors; and delivering the completed Project to Netflix in accordance with the approved technical, editorial and legal requirements.

7.2.3	The governance of the SPV shall vest in a Board of Directors consisting of two directors appointed by Infinity Films and two directors appointed by Idea Candy, unless the Parties explicitly agree in writing to amend the composition of the Board.

7.2.4	All decisions of the Board concerning any matter of material importance to the Project,  including changes to the budget, approval of overspend, reallocation of contingency funds, the hiring or dismissal of any Head of Department, any material amendments to the production schedule, the engagement of external legal, accounting or insurance services, and the approval of the Final Cost Report, shall require the unanimous approval of all directors serving on the Board.

7.3 	Development Budget and Expenditure

7.3.1	Once Netflix authorises a development budget, the Parties shall prepare a comprehensive and itemised Development Budget that identifies all anticipated development expenditure, including research costs; access and participation fees; Writers’ fees; preliminary legal opinions or risk assessments; travel and investigative expenses; archive-access costs; production-accounting set-up costs; development-producer fees; and all other deliverables and materials required by Netflix as part of the development phase.

7.3.2	No development expenditure shall exceed the amount approved in the Development Budget unless the Executive Producers unanimously approve such excess in writing, and unless written consent is obtained from Netflix in circumstances where Netflix’s approval is contractually or operationally required.

7.4 	Production Budget and Schedule

7.4.1	Following the commissioning of the Project, the Parties shall prepare a complete and detailed Production Budget using FilmAcc and/or Movie Magic Budgeting (MMB), which budget shall include all above-the-line costs, production costs, post-production expenses, archive-licensing costs, music-licensing costs, legal fees, insurance premiums, contingency amounts, and any COVID-related or risk-mitigation line items that are reasonably required under the circumstances.

7.4.2	The completed Production Budget shall be submitted to Netflix for formal approval, and no adjustment, revision or reallocation within the Production Budget shall be made unless Netflix provides express written approval and the Executive Producers unanimously approve such revision.

7.4.3	The Parties acknowledge and agree that contingency funds form part of the controlled financial structure of the Project and may only be utilised for genuinely unforeseeable, unavoidable and justified production costs. Contingency funds may not be used to achieve discretionary creative improvements or enhancements unless Netflix has granted prior written approval.

7.5 	Payment Structures and Cashflow Management

7.5.1	Netflix shall make payments to the SPV in accordance with a mutually agreed Payment Schedule, which Payment Schedule shall typically link payments to key production milestones, including the execution of the commissioning agreement, the commencement of principal photography, the commencement of post-production, the submission of fine cuts, the delivery of the final IMF master, and the submission and acceptance of the Final Cost Report.

7.5.2	The Line Producer shall ensure that cashflow projections are updated regularly and remain aligned with the Payment Schedule and shall further ensure that the SPV maintains sufficient liquidity at all times to meet ongoing production obligations.

7.5.3	The Parties agree that all payments made from the SPV bank account shall require the approval and signature of four authorised individuals, namely the Production Accountant, the Series Producer, the Line Producer, and one Executive Producer.

7.6 	Producer Fee and 50/50 Revenue Split

7.6.1	The Parties agree that the producer fee payable to the Producers upon commissioning of the Project shall be divided equally between Infinity Films and Idea Candy, and that each Party shall receive fifty percent (50%) of the total producer fee, irrespective of internal allocations among personnel.

7.6.2	Where Netflix requires the payment of specified Executive Producer fees or designated Producer-team fees, such fees shall be allocated in accordance with the roles, contributions and responsibilities described in this Agreement; however, such allocations shall not, in any manner, alter the Parties’ equal entitlement to the producer fee.

7.6.3	The Parties further agree that all future profit participation, backend revenue, licensing income or ancillary exploitation revenue arising from the Project, if applicable, shall be shared equally between Infinity Films and Idea Candy on a fifty-fifty (50/50) basis.

7.7 	Financial Reporting, Accounting and Reconciliation

7.7.1	The Line Producer and the Production Accountant shall prepare monthly financial reports that include cost-to-date summaries, cost-to-complete forecasts, projected final costs, variance analyses, cashflow statements, petty-cash reconciliations and trial balances, all prepared in accordance with recognised production accounting standards.

7.7.2	These monthly financial reports shall be submitted to the Executive Producers, to the Series Producer and to the designated Netflix Production Finance representative for review and oversight.

7.7.3	All accounting practices employed by the SPV shall comply with Netflix’s Audit and Compliance Guidelines, including, without limitation, the retention of all original receipts and purchase orders, the accurate categorisation of expenses, the tracking and verification of all invoices, adherence to payroll compliance, the vetting of suppliers, and the proper reconciliation of all bank accounts.

7.8 	Cost Overages and Overruns

7.8.1	No cost overrun may be incurred under any circumstances unless the Executive Producers unanimously approve such overrun and Netflix provides prior written approval confirming that the overrun is authorised.

7.8.2	If a cost overrun becomes unavoidable due to circumstances that are extraordinary, unforeseeable and outside the reasonable control of the Parties, the Parties shall prepare and submit a revised budget to Netflix and may not incur the overrun until Netflix has granted its written approval.

7.8.3	If a cost overrun arises due to the negligence, breach of duty or misconduct of any Party, such overrun shall be borne exclusively by the Party responsible for causing the overrun and shall not be charged to the SPV or to Netflix.

7.9 	Audit Rights

7.9.1	Netflix shall have the unrestricted right to audit the financial records of the SPV at any time during the production of the Project and for a period of at least seven (7) years following the delivery of the Project.

7.9.2	The Parties shall fully cooperate with all audit requests and shall provide Netflix with access to all invoices, contracts, receipts, payroll documentation, bank statements, production reports and any other financial records reasonably required to complete the audit.

7.9.3	If any financial irregularities or discrepancies are identified through such audit, the responsible Party shall immediately rectify the irregularities and indemnify both the SPV and Netflix for any resulting loss or liability.

7.10 	Final Cost Report and Financial Close-Out

7.10.1	Within thirty (30) days of the delivery of the completed Project to Netflix, the Line Producer and the Production Accountant shall prepare a Final Cost Report that reconciles all expenditure incurred during production and provides all supporting documentation required by Netflix.

7.10.2	The Final Cost Report shall be reviewed and approved by the Executive Producers, by the Series Producer and by Netflix’s Production Finance Department before any further payments to the Parties may be made.

7.10.3	No final producer-fee residuals, backend profit participations, revenue shares or any other financial entitlements due to the Parties shall be disbursed until Netflix has confirmed in writing that the Final Cost Report has been reviewed, accepted and is deemed contractually complete.

7.11	Joint and Several Liability

Infinity Films and Idea Candy agree that all warranties, indemnities, undertakings and obligations under this Agreement, and under any Development or Production Agreement concluded with Netflix, shall be binding upon them jointly and severally. Netflix or any beneficiary of such warranties shall be entitled to proceed against either Party without the need to join the other Party, and no release, indulgence or waiver granted to one Party shall affect the continuing liability of the other.

8. 	LIABILITY, WARRANTIES, INDEMNITIES, INSURANCE AND RISK ALLOCATION

8.1	 The Parties acknowledge that, although this Agreement contains references to narrative structure, editorial choices, storylines, thematic intentions, episode descriptions, contributor engagement plans and other creative elements, including those set out in clauses 1.15 to 1.18, clause 3, and the development materials described in clause 10.2, all such descriptions are indicative, non-binding and subject to creative evolution, investigative developments, editorial discretion and Netflix’s reasonable review requirements. Nothing in those clauses shall be interpreted as obliging either Party to adhere to any fixed editorial structure, storyline, episode sequence, contributor list, narrative device or creative treatment. All creative elements remain subject to refinement, adjustment or change during Development, Production and Post-Production, provided that Netflix’s legal, ethical and factual-accuracy requirements continue to be met.

8.2 	General Principles of Liability

8.2.1 	The Parties acknowledge that the production of a high-risk, true-crime documentary series of this nature entails significant legal, ethical, financial and reputational exposure, arising from, among other things, the handling of sensitive material, interaction with vulnerable contributors, engagement with law-enforcement officials, and reliance on archival and State-produced evidence.

8.2.2 	The Parties agree to adopt and maintain a comprehensive and proactive approach to risk management throughout development, pre-production, production and post-production, ensuring that all foreseeable risks are identified, mitigated, recorded and addressed in accordance with legal requirements, industry best practice and Netflix’s internal protocols.

8.3 	Warranties by Each Party

8.3.1 	Each Party warrants that it has the full legal right, authority and capacity to enter into and perform its obligations under this Agreement, and that nothing in this Agreement violates any law, contract, corporate restriction, court order or regulatory obligation binding upon it.

8.3.2  	Each Party warrants that all materials, creative contributions, research, footage, writings, concepts, designs, or other forms of intellectual property supplied or created by it shall be wholly original or lawfully acquired, and shall not infringe any copyright, trademark, personal right, privacy right, personality right or moral right of any third party.

8.3.3 	Each Party warrants that no defamation, false representation, negligent misstatement, breach of confidentiality or breach of privacy shall arise from its contributions to the Project.

8.3.4 	Each Party warrants that all Contributor Releases, archive licences, State-evidence permissions, location releases and any other rights documentation obtained by that Party shall be legally valid, accurate, comprehensive and fully enforceable.

8.3.5 	Each Party warrants that it shall at all times comply with all applicable laws, including the Film and Publications Act, the Protection of Personal Information Act (POPIA), the Criminal Procedure Act, all applicable copyright legislation, all relevant broadcasting standards, all laws governing vulnerable persons, and any additional requirements imposed by Netflix.

8.4 	Warranties Relating to Content Accuracy and Legal Safety

8.4.1 	The Parties warrant that all factual assertions made in the Project shall be substantiated by verified research, appropriate documentary evidence, credible eyewitness testimony, legally acquired archival materials, forensic reports, police documents, court rulings and, where necessary, expert opinions.

8.4.2 	The Parties warrant that no depiction in the Project shall be intentionally misleading, that no scene shall be edited in a manner that materially distorts factual accuracy, that no allegation shall be included without an appropriate factual basis, legal clearance or contextual justification, and that all obligations relating to balancing, fairness and contextualisation shall be met.

8.4.3	Where allegations or disputed facts are presented in the Project, the Parties shall ensure that such matters are clearly identified as disputed, that right-of-reply opportunities are offered where required, that all statements are presented in proper context, and that all contentious material is reviewed by legal counsel before inclusion.

8.5 	Warranties Relating to the Subject and Sensitive Material

8.5.1 	The Parties warrant that the portrayal of the Subject shall avoid glorification or sensationalism, shall accurately reflect the factual record, shall comply with any applicable court order, shall comply with ethical standards relating to the treatment of victims and perpetrators, and shall include contextual, balanced and legally reviewed commentary, while allowing the Parties to determine the final narrative approach, structure and emphasis in accordance with clause 3 of this agreement.

8.5.2 	The Parties warrant that no compensation of any nature shall be paid, whether directly or indirectly, to the Subject, and that the Project shall comply with South African laws and international principles that prohibit criminals from profiting from their notoriety.

8.6 	Indemnities

8.6.1 	Each Party (the “Indemnifying Party”) hereby indemnifies and holds harmless the other Party, the SPV, Netflix, and all of their respective officers, directors, employees, contractors and agents (collectively, the “Indemnified Parties”) from and against any and all losses, damages, claims, liabilities, fines, penalties, legal costs and expenses that arise from any breach of this Agreement, any breach of the warranties given in this Agreement, any infringement of intellectual-property rights, any breach of privacy or confidentiality, any breach of data-protection obligations, any unauthorised disclosures, any negligent, reckless or unlawful acts or omissions, any misrepresentation or false statements, any failure to obtain valid contributor releases or licences, or any defamation or injurious falsehood arising from content contributed by the Indemnifying Party.

8.6.2 	Each Party shall indemnify the other Party against any claims brought by contributors that arise from the negligent or improper handling of interviews, archival materials or sensitive content by that Party.

8.6.3 	Where a claim is caused jointly by both Parties, liability shall be apportioned between them according to their respective degrees of fault; provided that, where Netflix or the SPV suffer harm, both Parties shall remain jointly and severally liable unless a competent court determines otherwise.

8.7 	Third-Party Claims and Procedure

8.7.1 	Each Party shall notify the other Party in writing immediately upon becoming aware of any threatened claim, any actual claim, any allegation of defamation, privacy breach, copyright infringement or similar legal risk, or any subpoena, summons or legal demand relating to the Project.

8.7.2 	The Parties shall cooperate fully with one another, and with Netflix where applicable, in any investigation, defence, settlement negotiation or litigation relating to such claim.

8.7.3 	No Party may settle, compromise or otherwise dispose of any claim that affects the Project, the SPV or Netflix without the prior written approval of the other Party and, where required under the commissioning or production arrangements, the written approval of Netflix.

8.8 	Insurance Requirements

8.8.1 	The Parties shall obtain and maintain, for the duration of the Project and for any additional period required by Netflix, all insurances mandated by Netflix, including but not limited to comprehensive production insurance, public-liability insurance, employers’ liability insurance, workers’ compensation insurance, travel and equipment insurance, and Errors and Omissions (“E&O”) insurance with coverage limits acceptable to Netflix.

8.8.2 	The Parties shall ensure that the E&O insurance provides cover for claims arising from defamation, privacy breaches, infringement of intellectual-property rights, negligence in rights acquisition, unauthorised use of archival material, errors in portrayal and omissions in contextualisation.

8.8.3 	Each Party shall, upon request by Netflix or by the other Party, promptly provide certificates of insurance and any accompanying documentation necessary to demonstrate compliance with the insurance requirements in this Agreement.

8.9 	Financial Liability Limitations

8.9.1 	Except to the extent prohibited by law or where an express indemnity under this Agreement applies, neither Party shall be liable to the other Party for any consequential, indirect or special loss or damage, including any loss of profits or punitive damages.

8.9.2	 The limitation of liability set out in clause 8.9.1 shall not apply to any liability arising from intellectual-property infringement, breach of confidentiality, breach of data-protection obligations, fraud, intentional misconduct, gross negligence or breach of warranties.

8.10 	Risk Allocation Relating to Archive and Sensitive Material

8.10.1 	Each Party shall bear full responsibility for ensuring the legality, accuracy, proper licensing and legal safety of any archival, digital, forensic or other third-party material sourced by that Party for the purposes of the Project.

8.10.2 	If any archival or sensitive material introduced into the Project by a Party is subsequently found to be defective, unlicensed, unlawfully obtained or otherwise unlawful to use, that Party shall, at its own cost and risk, ensure that such material is removed or replaced and shall remedy any associated harm or exposure.

8.11 	Obligation to Mitigate Risk

8.11.1 	Each Party shall take all reasonable steps to prevent the occurrence or escalation of any legal, financial, ethical or security risk in connection with the Project, including by ensuring appropriate legal review, factual verification, rights-clearance checks, contributor vetting, safe storage of sensitive materials, strict access controls and secure data handling.

8.11.2	 A Party’s failure to take reasonable steps to mitigate foreseeable risks shall constitute a breach of this Agreement.

- CONFIDENTIALITY, DATA PROTECTION, INVESTIGATION SECURITY AND HANDLING OF SENSITIVE MATERIAL

9.1 	General Confidentiality Obligations

9.1.1 	Each Party undertakes to keep strictly confidential all information obtained in connection with the Project, including investigative information, forensic materials, contributor identities, private archives, unpublished research, legal opinions, police documents, court records that are not in the public domain, internal Netflix communications, proprietary formats, structures and treatments, and any other information that is expressly marked as confidential or would reasonably be understood to be confidential by its nature or context.

9.1.2 	No confidential information may be disclosed by either Party to any person except to employees or contractors who require access in order to perform their duties in connection with the Project, to the Parties’ or the SPV’s legal counsel, to authorised Netflix representatives, to auditors, to insurers, or where disclosure is required by law or by a valid court order.

9.1.3	 Each Party shall ensure that every person who receives confidential information under clause 9.1.2 is bound by written confidentiality obligations that are at least equivalent in scope and strictness to the confidentiality obligations contained in this Agreement.

9.2 	Confidentiality Regarding the Subject and Victims

9.2.1 	The Parties acknowledge that the Project involves deeply sensitive personal histories relating to the Subject, Zaheera Boomgaard (who is also known under the aliases Penny Basdeo, Penny Wookey, Penny Boomgaard, Sabrina Boomgaard and Zaheera Wookey), as well as to victims who were murdered or harmed, members of the victims’ families, witnesses and neighbours, investigative officials and other individuals who have been traumatised by the Subject’s conduct or by the events depicted.

9.2.2 	The Parties agree that no personal details, allegations, investigative findings or emotionally sensitive content relating to any of these individuals shall be disclosed to any third party outside the scope of the production of the Project, save as strictly required for lawful production, legal or commissioning purposes.

9.2.3 	The Parties shall adopt and maintain special precautions when handling information that could cause distress, reputational harm or further psychological trauma to any individual, and shall ensure that such information is treated with heightened sensitivity and discretion.

9.3 	Handling of Police, Forensic and State Evidence

9.3.1 	The Parties acknowledge that the Project may involve access to State documents and evidence, including SAPS case files, forensic laboratory results, forensic diagrams and metadata reports, fingerprints, toxicology reports and autopsy reports (where access is lawfully granted), CCTV footage obtained through SAPS channels, private-investigator reports, court transcripts, warning statements and photographs originating from crime scenes or mortuaries.

9.3.2 	All such State evidence shall be handled strictly in accordance with South African legislation, SAPS protocols, any applicable directives from the National Prosecuting Authority, any court-ordered restrictions, POPIA, and any specific conditions imposed by the original custodians or authorities controlling such evidence.

9.3.3	 No Party may disclose, publish or use State evidence outside the context of the Project unless such disclosure, publication or use is expressly authorised in writing by the lawful authority that controls the evidence and, where applicable, by Netflix.

9.4 	Storage, Encryption and Data Security

9.4.1 	All digital and physical materials relating to the Project shall be stored using secure, encrypted and access-controlled systems that comply with Netflix’s Security and Asset Protection Policies and any other applicable Netflix security standards notified to the Parties from time to time.

9.4.2 	The Parties shall ensure that, at a minimum, files are stored only on encrypted drives that comply with Netflix’s certification requirements, that cloud storage is used only where pre-approved in writing by Netflix, that no materials are stored on personal devices, that passwords used for access are strong, unique and updated regularly, and that multi-factor or dual-factor authentication is enabled wherever reasonably possible.

9.4.3 	The Parties shall ensure that especially sensitive materials are compartmentalised and that access to such materials is restricted to specifically authorised persons on a strict need-to-know basis.

9.5 	Popia Compliance and Personal Data Protection

9.5.1 	Each Party shall comply fully with the Protection of Personal Information Act (POPIA), including obligations relating to the lawful collection of personal data, the processing of such data for legitimate documentary and journalistic purposes, the minimisation of data usage, the secure storage and limited retention of personal data, and the destruction or de-identification of data once it is no longer required for the Project or for legal purposes.

9.5.2 	In applying POPIA, each Party shall take into account the Project’s legitimate public-interest purpose, which includes the documentation of criminal activity, systemic failures, forensic investigations, victim narratives and issues of public safety, and shall balance privacy rights against this public-interest mandate in accordance with applicable law.

9.5.3 	Special categories of personal data, including medical, psychiatric or criminal-record information, shall be processed only where such processing is legally permissible, editorially or journalistically necessary, supported by an appropriate contributor release or lawful access permission, and subject to robust safeguards against misuse, unauthorised disclosure or improper secondary use.

9.6 	Third-Party access and Sharing Restrictions

9.6.1 	No Party may transfer, share, supply or disclose any production materials, whether raw or edited, to media organisations, other production companies, journalists, external researchers, social-media platforms, family members of contributors, private investigators or any other unauthorised third party.

9.6.2 	Exceptions to the restriction in clause 9.6.1 may only be made where the disclosing Party has obtained the prior written approval of the other Party, the prior written approval of Netflix, and, where appropriate, the prior written confirmation of legal counsel that such disclosure is lawful and consistent with this Agreement.

9.7 	Investigation Security and Non-Disclosure of Editorial Lines

9.7.1 	The Parties acknowledge that any premature disclosure of editorial direction,

investigative findings or narrative structure may compromise the safety of contributors, interfere with law-enforcement processes, prejudice the reputational rights of individuals, or undermine the integrity and impact of the Project.

9.7.2 	Accordingly, no Party shall share any internal editorial documents, including outlines, story structures, character maps, scripts, interview notes, cut summaries or episode breakdowns, with any third party not expressly authorised under this Agreement or by Netflix.

9.7.3	For the avoidance of doubt, the internal editorial documents referenced in this clause, including outlines, story structures and episode breakdowns, are developmental tools and shall not be construed as final or binding creative commitments.

9.8 	Breach of Confidentiality

9.8.1	Any breach of the confidentiality obligations set out in this Agreement by either Party, or by any employee, contractor or representative of a Party, shall constitute a material breach of this Agreement.

9.8.2 	In the event of such a breach, the breaching Party shall immediately notify the other Party, shall take all reasonable steps to mitigate the effects of the breach, shall compensate the other Party and the SPV for any resulting harm, shall cooperate fully with any security or compliance investigation initiated by Netflix, and shall take all reasonable remedial measures to prevent a recurrence of the breach.

9.9 	Return and Destruction of Sensitive Materials

9.9.1 	Upon completion of the Project, or upon written request by Netflix, each Party shall promptly return all confidential material in its possession to the appropriate Party or custodian, shall delete all digital copies of such material from its systems, shall provide written certification that such deletion or destruction has occurred, and shall retain only such materials as are required to be kept by law or by express written agreement with Netflix.

9.9.2 	Any materials that must be retained for legal, regulatory or audit purposes shall be stored securely for the statutory or contractually required retention period and shall remain subject to the confidentiality and data-security obligations in this Agreement for as long as they are held.

9.10 	Permitted Disclosure

9.10.1 	Disclosure of confidential information or sensitive materials shall be permitted only

where such disclosure is required by a valid court order, by SAPS or prosecuting   authorities, by Netflix for legitimate commissioning, legal or compliance purposes, or to comply with applicable statutory obligations.

9.10.2 	Where a Party is required by law or legal process to disclose confidential information, that Party must notify the other Party and Netflix immediately upon receiving the legal demand, must disclose only that information which is strictly required in order to comply with the legal obligation, and must cooperate with the other Party and with Netflix in taking any steps reasonably available to protect confidentiality to the fullest extent permitted by law.

.

10. 	NETFLIX DELIVERABLES, DEVELOPMENT DELIVERABLES, REPORTING OBLIGATIONS AND CREATIVE/LEGAL SIGN-OFF PROCEDURES

10.1 		General Obligation to Produce and Deliver Materials

10.1.1 	The Parties acknowledge and agree that the commissioning of the Project by Netflix

requires strict adherence to a comprehensive framework of deliverables, review stages, approvals, documentation, reporting obligations and legal compliance. The Parties therefore undertake to prepare, compile and deliver all development, creative, financial, editorial, technical and legal materials described in this clause 10 in accordance with the timelines, technical specifications and approval procedures required by Netflix.

10.1.2 	All deliverables referenced herein shall be supplied to Netflix in the form, format, technical specification and through the secure delivery channels stipulated by Netflix.

10.1.3 	No deliverable shall be deemed submitted unless Netflix confirms receipt in writing through the designated Netflix representative(s).

10.2 	Development Deliverables Required by Netflix

The Parties shall jointly prepare and deliver to Netflix, during the development phase, a comprehensive suite of development materials (collectively referred to as the “Development Package”), which shall form an essential component of Netflix’s evaluation of the Project. The Development Package shall be prepared in accordance with professional documentary standards and Netflix’s requirements and shall reflect the Parties’ then-current creative intentions, it being recorded that such materials may be refined, expanded or adjusted in the ordinary course of development, subject to Netflix’s review and approval process.

10.2.1 	Detailed editorial and story structure document

The Parties shall prepare and deliver a fully developed editorial and story-structure document consisting of complete written sentences that clearly describe, on a non-binding and indicative basis, the then-envisaged narrative arcs of the Project, the thematic pillars underpinning the series, the proposed structure of all three episodes, the unique editorial angle of the Project, the central mysteries and dramatic questions driving viewer engagement, the intended multi-timeline approach, the emotional spine of the narrative and the anticipated narrative outcomes, it being acknowledged that such structure may be revised or reconfigured during Development, Production and Post-Production, subject to Netflix’s review rights.

10.2.2 	Complete character participation matrix

The Parties shall compile and deliver a complete character-participation matrix that identifies, with specificity and justification, all key individuals whose participation is currently intended to be secured for on-camera contribution, including but not limited to the families of victims, investigators, specialists, witnesses, journalists, individuals connected to the Subject and any other contributors whose inclusion is regarded as important for the integrity and completeness of the story, it being understood that actual participation shall at all times remain subject to availability, consent and legal and ethical considerations.

10.2.3 	Wish-list of aspirational contributors

The Parties shall prepare a written list identifying all aspirational contributors whose participation would materially enhance the Project, including individuals whose access is difficult to secure or whose involvement may only become possible should new investigative pathways or permissions arise.

10.2.4 	Confirmation of access to key archival footage

The Parties shall prepare a written memorandum setting out, in detail, all archival footage and evidentiary materials obtained to date, including police files, digital evidence, personal and family archives, metadata logs, CCTV recordings, still photographs, WhatsApp logs, financial records and court transcripts, and shall attach evidence of all rights, permissions and licences obtained in respect thereof.

10.2.5 	Wish-list of hard-to-obtain archival footage

The Parties shall prepare a written list identifying any archival material that remains desired but not yet secured, which shall include, where applicable, footage or records held by Sterkfontein Psychiatric Hospital, historical family archives, materials originating in foreign jurisdictions and documentary evidence controlled by third parties.

10.2.6 	Overview of required IP clearances

The Parties shall provide a written schedule identifying all third-party copyrighted materials proposed for inclusion, all image rights requiring clearance, all music or photographs that may require negotiation, any State documents that require special permissions and any international archives that require cross-border or special licensing arrangements.

10.2.7 	Overview of personal archive access

The Parties shall prepare a detailed report setting out all personal archives made available to the production, including archives provided by families of victims, neighbours, former friends of the Subject, access to digital archives extracted from devices lawfully, and any letters, messages or journals contributed for use in the Project.

10.2.8 	Producer’s due-diligence plan

The Parties shall prepare a complete due-diligence outline that describes, in full detail, the process by which the Producers intend to verify the accuracy of all factual claims, including the use of a structured fact-checking protocol, reliance on metadata verification, corroboration of dates and timelines, cross-referencing of records and logs, review of police reports and other steps reasonably required to ensure factual accuracy and legal safety.

10.2.9 	List of suggested directors

The Parties shall prepare a written document identifying the directors recommended for consideration, including links to their previous work, a summary of their editorial philosophy, their availability for the Project and a description of their creative approach, it being recorded that this list is a development-planning tool only and does not in itself constitute any appointment, which shall be made in accordance with this Agreement and Netflix’s approval processes.

10.2.10 	List of suggested HODs

The Parties shall prepare a written list of recommended Heads of Department for the Project, including without limitation the Lead Editor, Showrunner, Archive Researcher, Cinematographer, Legal Liaison, Finance Controller and Sound Designer, together with supporting rationale for each proposed appointment.

10.2.11 	Comprehensive legal opinion

The Parties shall procure and deliver a comprehensive written legal opinion prepared by Production Counsel, which shall address all material legal issues including defamation risk, compliance with POPIA, any implications arising from criminal-procedure legislation, the lawful use of State evidence, the lawful portrayal of the Subject, the fulfilment of right-of-reply obligations and the ethical representation of traumatised victims.

10.2.12 	Appointment of Netflix-approved legal counsel

The Parties shall provide written proof that  Willem De Klerk Attorneys has been formally appointed as Production Counsel for the Project, as required by Netflix, and that no deviation from this appointment has occurred without Netflix’s prior written approval.

10.2.13 	Production Counsel briefing document

The Parties shall prepare and deliver a briefing document summarising all legal issues that require the specialised attention of Production Counsel, including matters relating to prison-access protocols, the legal constraints governing compensation of criminals, the handling of sealed documents, the protection of minors, the boundaries of cooperation with police authorities and the management of high-risk portrayals.

10.2.14	Producer’s research and development questionnaire

The Parties shall prepare a written document containing all questions, uncertainties, risks, factual gaps and investigative leads identified during development, and this questionnaire shall be updated on a continuing basis as the development process progresses.

10.2.15 	Additional materials requested by Netflix

The Parties acknowledge that Netflix may, in its discretion, request supplementary materials that are reasonably necessary for assessing the Project’s feasibility, factual accuracy, creative approach or legal and reputational risk, and the Parties shall supply any such materials promptly and in full.

10.3 	Reporting Obligations during Development

10.3.1	The Parties shall provide Netflix with weekly written reports during the development phase, which shall include a comprehensive summary of the progress of research activities, all developments relating to contributor access, any legal risks identified, any editorial or factual discoveries that may influence the Project and any delays or anticipated delays that may affect the development timeline.

10.3.2 	All weekly reports shall be transmitted to Netflix by email and shall also be uploaded to the secure Netflix production repository designated for the Project.

10.4 	Creative Approvals and Sign-Off Procedures

10.4.1 	The Parties acknowledge that Netflix shall have approval rights over all key creative elements of the Project, including the episode outlines, the selection of the Director, all principal casting decisions, the appointment of key Heads of Department, the musical direction, the title design, any proposed use of sensitive imagery and any proposed revisions to the narrative structure.

10.4.2 	The Parties agree that no material change may be made to the creative direction, editorial structure, narrative approach or visual treatment of the Project without the prior written approval of Netflix.

10.5 	Legal Sign-Off Procedures

10.5.1	Production Counsel shall conduct formal legal reviews at each of the following milestones: each episode outline, each rough cut, each locked cut and the final delivery of the Project.

10.5.2 	The Parties shall not submit any episode, cut or related material to Netflix unless Production Counsel has first issued written confirmation that the relevant material has passed legal clearance.

10.6 	Production Deliverables During Shooting

10.6.1	During principal photography, the Producers shall, upon request by Netflix, provide all production deliverables reasonably required for oversight, including weekly call sheets, an updated production schedule, applicable risk assessments, daily production reports, contributor-status updates, updates on archive acquisition and preliminary legal-clearance notes.

10.7 	Post-Production Deliverables Prior to Delivery

10.7.1		The Producers shall submit, for Netflix’s review at each corresponding stage of post-production, the assemblies, rough cuts, fine cuts and locked cuts of each episode, together with the relevant QC reports, written legal-clearance letters, music cue sheets, graphic-package deliverables and drafts of subtitles (where applicable).

10.8 	Final Delivery Deliverables

10.8.1

Upon completion of post-production, the Producers shall deliver to Netflix all final deliverables required by Netflix in terms of its commissioning agreement and technical delivery specifications, together with any additional legal, editorial, technical or financial documentation reasonably required by Netflix as part of its final acceptance procedures.

10.8.2	Final delivery shall not be deemed complete unless and until Netflix has issued written confirmation of its acceptance of all required deliverables.

11.	COMPREHENSIVE RISK MANAGEMENT FRAMEWORK, LEGAL RISK

MITIGATION AND ETHICAL COMPLIANCE

11.1 	General Risk-Management Obligations

11.1.1 	The Parties acknowledge that the Project involves significant legal, ethical,

reputational and security risks, and they therefore agree to adopt a comprehensive,

documented and continuously updated risk-management framework for all phases of the Project.

11.1.2 		The Parties shall ensure that all reasonably foreseeable risks are identified, assessed, recorded and mitigated through appropriate measures, including the involvement of Production Counsel, the implementation of Netflix’s risk protocols and the adoption of internal escalation procedures.

11.1.3 	Each Party shall ensure that its employees, contractors and representatives are	 made aware of the risk profile of the Project and are trained or briefed appropriately in respect of confidentiality, contributor care, evidence handling, data protection, security protocols and ethical obligations.

11.1.4 	The Parties shall hold regular risk-review meetings during Development, Pre-

Production, Production and Post-Production, at which they shall review new developments, allegations, archival discoveries, contributor concerns and legal advice, and shall adjust the risk-management framework accordingly.

11.2 	Defamation, Reputation and Portrayal Risk

11.2.1 	The Parties acknowledge that the Project may contain serious allegations, contested narratives and highly sensitive personal information, the publication or broadcast of which could expose the Parties, the SPV and Netflix to defamation and reputational-harm claims.

11.2.2	In order to mitigate defamation and portrayal risk, the Parties shall:

(a) 	ensure that all serious allegations are supported by documentary evidence,

credible testimony or clearly indicated investigative context;

(b) 	present allegations as allegations where they have not been proven in a court

of law;

(c) 	avoid making gratuitous or speculative assertions that exceed the available

evidence;

(d) 	afford right-of-reply opportunities where required and reasonably practicable;

And

(e) 	submit all high-risk material for prior legal review by Production Counsel.

11.2.3 	The Parties shall ensure that the portrayal of identifiable individuals, including the Subject, victims, family members, investigators, neighbours and any other contributor, is fair, balanced and contextual, and that no editing choice materially misrepresents their words, conduct or involvement.

11.2.4 	Where Production Counsel identifies a defamation or portrayal risk that requires modification, removal, rephrasing or further contextualisation of content, the Parties shall implement such recommendations in full, unless Netflix and Production Counsel agree in writing to an alternative approach that is legally safe.

11.3 	Privacy, POPIA and Data-Protection Compliance

11.3.1 	The Parties acknowledge that the Project involves the processing of personal

information, special personal information and potentially sensitive records (including medical, psychiatric, criminal, financial and family information) and that such processing is subject to POPIA and other applicable data-protection laws.

11.3.2 	Each Party shall ensure that personal information is collected lawfully, processed for legitimate documentary and journalistic purposes, used only to the extent necessary for the Project, stored securely, retained only for as long as reasonably required and destroyed or de-identified once no longer needed for legal or production purposes.

11.3.3 	The Parties shall implement appropriate technical and organisational measures to secure personal data against loss, unauthorised access, unlawful processing, alteration or disclosure, including encryption, access controls, password discipline, multi-factor authentication and secure transfer protocols.

11.3.4 	The Parties shall ensure that any cross-border transfer of personal information (for example between South Africa, the United Kingdom, India and Netflix’s international infrastructure) complies with applicable data-transfer requirements under POPIA, the UK GDPR and any other relevant regime, and is carried out only under appropriate safeguards.

11.4 	Interface with Criminal Proceedings, SAPS and the Courts

11.4.1	The Parties acknowledge that the subject matter of the Project intersects with historic and potentially ongoing criminal investigations, prosecutions, appeals or inquests, and they therefore undertake to comply strictly with applicable criminal-procedure rules, contempt-of-court principles and fair-trial protections.

11.4.2 	The Parties shall avoid publishing or depicting any material that could unlawfully prejudice pending or reasonably foreseeable legal proceedings, could amount to contempt of court or could improperly interfere with law-enforcement processes, and they shall seek legal advice whenever doubt exists.

11.4.3 	The Parties shall co-operate with SAPS, the National Prosecuting Authority and any relevant court, to the extent required by law, and shall respect all conditions, undertakings or restrictions imposed in relation to access to case files, evidence, transcripts or other sensitive material.

11.4.4 	Where any law-enforcement or prosecutorial authority raises a substantiated concern regarding the timing, content or framing of particular material, the Parties shall promptly escalate such concern to Production Counsel and Netflix for resolution and shall act in accordance with the agreed legal guidance.

11.5 	Editorial Safeguards, Disclaimers and On-Screen Clarifications

11.5.1 	The Parties agree that, where appropriate, the Project shall make use of on-screen disclaimers, contextual notes and clarificatory text in order to indicate where facts remain disputed, where investigations are ongoing, where allegations have not resulted in convictions, or where editorial reconstruction is being used for illustrative purposes.

11.5.2 	The Parties shall ensure that editorial devices such as voice-over, captions, on-screen text, graphics or legal disclaimers are deployed in a manner that promotes clarity and prevents viewers from drawing inaccurate inferences about individuals or events.

11.5.3  	The Parties shall ensure that any reconstructed or stylised sequences are clearly distinguishable from documentary footage and that viewers are not misled into believing that such sequences constitute actual evidentiary material.

11.6 	Escalation to Legal Counsel and Netflix

11.6.1 	Whenever a material legal, ethical or reputational risk is identified by any member of the creative team, crew or production staff, that risk shall be escalated without delay to the Series Producer, the Executive Producers and Production Counsel.

11.6.2 	The Parties shall not ignore, minimise or conceal any credible legal or ethical concern relating to the Project, whether raised internally, by a contributor, by an external party or by Netflix, and shall instead treat such concerns as triggers for immediate review and mitigation.

11.6.3 	Where Production Counsel and Netflix jointly determine that particular content, an interview, a sequence or an episode requires modification, delay or removal in order to mitigate risk, the Parties shall comply with such determination and shall adjust the creative approach accordingly.

11.7 	Netflix Ethics, Respect and Dignity Standards

11.7.1 	The Parties acknowledge that Netflix maintains internal ethics, respect and dignity guidelines applicable to documentary content, including guidelines relating to the treatment of victims, vulnerable persons, traumatised contributors, minors, law-enforcement officials, incarcerated individuals and individuals with mental-health vulnerabilities.

11.7.2 	The Parties shall ensure that all production, editorial and post-production decisions are tested against Netflix’s ethics and dignity guidelines and that, where there is any tension between dramatic impact and ethical treatment, ethical treatment shall prevail.

11.7.3 	The Parties shall immediately report to Netflix any incident of alleged harassment, exploitation, discrimination, abuse or unethical conduct by any member of the production team, and they shall co-operate fully with any investigation, corrective action or remedial steps required by Netflix or by law.

- TERM, SUSPENSION AND TERMINATION

12.1 	Term of the Agreement

12.1.1 	This Agreement shall commence on the date of signature by the last Party to sign and shall remain in force until the earlier of:
(a) 	the completion of all obligations arising from the commissioning, production

and delivery of the Project to Netflix;
(b) 	the lawful termination of the Project by Netflix under its commissioning

agreement; or
(c) 	the lawful termination of this Agreement in accordance with its provisions.

12.1.2 	Notwithstanding termination for any reason, the provisions of this Agreement that by their nature are intended to survive termination – including those relating to intellectual property, confidentiality, data protection, warranties, indemnities, risk allocation, dispute resolution and governing law – shall remain of full force and effect.

12.2 	Suspension

12.2.1	 If Netflix suspends development, production or delivery of the Project in terms of its commissioning arrangements, the Parties shall be deemed to be in a corresponding period of suspension under this Agreement and shall immediately scale down work to the level reasonably required to secure materials, protect data, preserve evidence and maintain contractual compliance.

12.2.2 	During any period of suspension, the Parties shall comply with all instructions issued by Netflix regarding the preservation of assets, the status of contributors, the handling of materials and the continuation or cessation of particular activities.

12.3 	Termination for Cause

12.3.1 	Either Party may terminate this Agreement with immediate effect by written notice to the other Party if the other Party commits a material breach of this Agreement and fails to remedy such breach within fourteen (14) calendar days after receipt of written notice calling upon it to do so, or within such longer remedial period as may reasonably be agreed in writing.

12.3.2 	A material breach shall include, without limitation:
(a) 	a serious or repeated violation of confidentiality or data-protection obligations;
(b) 	a serious or repeated violation of Netflix’s security or ethical standards;
(c) 	fraud, dishonesty or wilful misconduct;
(d) 	misappropriation or unauthorised use of Project funds or assets;
(e) 	failure to comply with legal-safety requirements in a manner that exposes the

Project or Netflix to undue risk;

(f) 	persistent failure to perform material obligations despite reasonable written

warnings.

12.3.3 	If this Agreement is terminated for cause, the non-breaching Party shall be entitled,

in addition to any other remedies at law, to claim damages, to seek specific performance and to require the breaching Party to co-operate fully in the orderly handover of materials, contracts and responsibilities.

12.4 	Termination Linked to Netflix Commissioning

12.4.1 	If Netflix elects not to commission the Project after Development, this Agreement shall continue to regulate the Parties’ rights and obligations in relation to development materials, intellectual property, confidentiality, risk allocation and any agreed development payments, but the production-specific provisions shall not come into operation.

12.4.2 	If Netflix terminates the commissioning or production agreement with the SPV for reasons not attributable to a breach by either Party, the Parties shall co-operate in good faith to:

(a) 	comply with all close-out obligations owed to Netflix;

(b) 	settle all lawful third-party claims and liabilities of the SPV to the extent

covered by Netflix payments; and

(c) 	agree on the future status of the Project and its materials, subject always to

any continuing rights held by Netflix.

- BREACH, REMEDIES AND SPECIFIC PERFORMANCE

13.1 	General Consequences of Breach

13.1.1 	If any Party breaches any provision of this Agreement, the other Party shall be

entitled to all remedies available in law or equity, including but not limited to damages, specific performance, interdictory relief and any other appropriate remedy, whether such remedies are expressly specified herein.

13.1.2 	The Parties acknowledge that certain breaches – including breaches relating to

confidentiality, data security, intellectual property, legal compliance and Netflix deliverables – may cause irreparable harm that cannot be adequately remedied by damages alone, and they therefore agree that the non-breaching Party and/or Netflix shall be entitled to urgent interdictory or injunctive relief.

13.2 	Duty to Mitigate

Each Party shall take all reasonable steps to mitigate any loss, damage or prejudice that it may suffer as a result of a breach by the other Party, and shall not be entitled to recover any loss that could reasonably have been avoided through such mitigation.

13.3 	Third-Party Claims

Where a breach of this Agreement by one Party results in a third-party claim against the SPV, Netflix or the other Party, the breaching Party shall remain liable in accordance with the indemnity and risk-allocation provisions of this Agreement, without prejudice to any additional remedies available at law.

- FORCE MAJEURE

14.1 	Definition and Effect

14.1.1 	A “Force Majeure Event” means any event or circumstance beyond the reasonable control of the affected Party that renders performance of its obligations impossible or impracticable, including but not limited to natural disasters, acts of God, war, terrorism, civil unrest, riots, strikes (other than strikes of the affected Party’s own employees), governmental restrictions, epidemics, pandemics, general power failures, network outages or the sudden unavailability of key locations due to law-enforcement actions or court orders.

14.1.2 	If a Party is prevented or delayed from performing its obligations due to a Force Majeure Event, that Party shall not be deemed to be in breach of this Agreement for so long as the Force Majeure Event persists and affects performance, provided that it complies with its obligations in clause 14.2.

14.2 	Notification and Mitigation

14.2.1 	The affected Party shall notify the other Party and Netflix in writing as soon as

reasonably possible after becoming aware of a Force Majeure Event, shall describe the nature and expected duration of the event, and shall keep the other Party reasonably informed of developments.

14.2.2 	The affected Party shall use all commercially reasonable endeavours to mitigate the

effects of the Force Majeure Event and to resume full performance as soon as reasonably practicable.

14.2.3		If a Force Majeure Event continues for a period exceeding sixty (60) consecutive

days, the Parties shall consult with Netflix in good faith regarding the continuation, modification or termination of the Project, and any Party shall be entitled, subject to Netflix’s commissioning arrangements, to terminate this Agreement on written notice without liability (save for accrued rights and obligations).

- DISPUTE RESOLUTION, GOVERNING LAW AND JURISDICTION

15.1 	Governing Law

This Agreement, and any dispute arising out of or in connection with it, shall be governed by, and interpreted in accordance with, the laws of the Republic of South Africa.

15.2 	Good-Faith Negotiation

15.2.1 	If any dispute arises between the Parties in connection with this Agreement, the

Parties shall first endeavour to resolve the dispute through good-faith negotiations between their respective Executive Producers or other designated senior representatives.

15.2.2 	If the dispute is not resolved within twenty (20) business days after written notice of the dispute is delivered by one Party to the other, either Party may refer the dispute to mediation or to the High Court as contemplated below.

15.3 	Jurisdiction

15.3.1 	Subject to any mandatory mediation or arbitration requirements that may be agreed in writing with Netflix, the Parties consent to the non-exclusive jurisdiction of the High Court of South Africa (Western Cape Division, Cape Town) in respect of any legal proceedings arising from or connected with this Agreement.

15.3.2 	Nothing in this clause shall prevent either Party or Netflix from seeking urgent injunctive or interdictory relief in any court of competent jurisdiction.

- NOTICES AND DOMICILIA

16.1 	Domicilium Addresses

16.1.1 	For all purposes arising from or in connection with this Agreement (including the

giving of notices and the serving of legal process), each Party chooses as its

domicilium citandi et executandi (“domicilium”) the physical address set out for that Party in clause 1 of this Agreement, marked for the attention of the Executive Producers of that Party.

16.1.2 	Either Party may change its domicilium to another physical address or email address in the Republic of South Africa on thirty (30) days’ written notice to the other Party, provided that the new domicilium is not a post office box and is a place where service of legal process may be effected.

16.2 	Delivery of Notices

16.2.1	Any notice or communication given under this Agreement shall be valid and

effective only if it is in writing and delivered by hand, sent by courier, transmitted by email or delivered by any other method expressly agreed in writing by the Parties.

    - A notice shall be deemed to have been received:

(a) 	on the date of delivery, if delivered by hand or courier during normal business

hours;

(b) 	on the first business day following transmission, if sent by email (unless the

sender receives an automated non-delivery notification); or

(c) 	on the date actually received, if delivered in any other lawful manner.

16.2.3 	Notwithstanding anything to the contrary, any notice given in connection with legal proceedings or the termination of this Agreement shall be delivered by hand or courier to the recipient’s physical domicilium address.

- CESSION, ASSIGNMENT AND DELEGATION

17.1 	Restrictions on Assignment

17.1.1 	No Party may cede, assign, transfer or delegate any of its rights or obligations

under this Agreement to any third party without the prior written consent of the other Party, which consent shall not be unreasonably withheld or delayed, and without obtaining any approvals required by Netflix.

17.1.2 	Notwithstanding clause 17.1.1, the Parties acknowledge that rights and obligations may be transferred to the SPV in terms of this Agreement and that Netflix may require specific assignments or novations as a condition of commissioning.

17.2 	Binding Effect

Subject to the foregoing, this Agreement shall be binding upon and shall inure for the benefit of the Parties and their lawful successors and permitted assigns.

- RELATIONSHIP BETWEEN THE PARTIES

18.1 	Independent Contractors

18.1.1 	The relationship between Infinity Films and Idea Candy in terms of this Agreement is that of independent contracting producers and co-producers, and nothing in this Agreement shall be construed as creating a partnership, joint venture (save for the contemplated SPV), agency, employment relationship or fiduciary duty between them beyond the express terms hereof.

18.1.2 	No Party shall hold itself out as the agent of the other Party, nor shall any Party incur any liability or obligation on behalf of the other Party, except as expressly provided in this Agreement or in any subsequent written agreement.

- GENERAL

19.1 	Whole Agreement

19.1.1 	This Agreement constitutes the entire agreement between the Parties in relation to its subject matter and supersedes all prior drafts, negotiations, understandings and agreements (whether written or oral) between them relating to the same subject matter.

19.2 	Variations

19.2.1 	No addition to, variation of or agreed cancellation of this Agreement shall be of any force or effect unless it is in writing and signed by duly authorised representatives of both Parties and, where required, approved by Netflix.

19.3 	Waiver

No relaxation, indulgence or extension of time granted by either Party to the other shall constitute a waiver of any of that Party’s rights in terms of this Agreement, nor shall it operate as an estoppel against that Party or preclude it from exercising any of its rights in the future.

19.4 	Severability

If any provision of this Agreement is found by a court of competent jurisdiction to be invalid, unlawful or unenforceable, such provision shall be severed from the Agreement to the extent of its invalidity, and the remaining provisions shall continue to be of full force and effect, provided that the Parties shall in good faith negotiate a replacement provision that most closely reflects the original intent in a lawful manner.

19.5 	Counterparts and Electronic Signatures

19.5.1 	This Agreement may be executed in counterparts, each of which shall be deemed an original, and all of which together shall constitute one and the same agreement.

19.5.2 	Signatures transmitted electronically (including scanned signatures and digitally authenticated signatures) shall, to the fullest extent permitted by law, have the same legal effect as original handwritten signatures.

19.6 	Costs

Each Party shall bear its own legal and professional costs incurred in the negotiation and preparation of this Agreement, unless otherwise agreed in writing or provided for in a commissioning or production agreement with Netflix.

Signed at ______________________ on this _____ day of _________________	_ 20_____

For and on behalf of
INFINITY FILMS (PTY) LTD

Name: ___________________________
Capacity: _________________________
Who warrants that he/she is duly authorised hereto.

Signed at ________________________ on this _____ day of _______________	_ 20_____

For and on behalf of
IDEA CANDY (PTY) LTD

Name: ___________________________
Capacity: _________________________
Who warrants that he/she is duly authorised hereto.